## Top Sheet
INSPECTION AND WORK REQUEST | [7 empty] | 60/RNDC/WP101B/TB-IWR-ST-017
Project: | The BenCab |  |  |  | Reference Number: |  | 60/RNDC/WP101B/TB-IWR-ST-017 | TRADES
[5 empty] | Date Prepared: |  | 2024-01-08 | MECHANICAL | M
[8 empty] | ELECTRICAL | E
Work Activity: |  | Concrete Pouring Request |  |  | Level: |  | Ground Floor | PLUMBING | PL
[8 empty] | FIRE PROTECTION | FP
[8 empty] | STRUCTURAL | ST
Location: | Zone 17 - FBB/1BB-2BB Zone 18 - LBB/1BB-2BB Zone 19 - MBB/1BB-3BB | [6 empty] | ARCHITECTURAL | A
Structure: | Shearwall | [6 empty] | LANDSCAPE | L
[8 empty] | INTERIOR DESIGN | ID
Trade: |  | Inspected By: Subcontractor | Checklist Form Reference Number | Inspected By: RNDC |  |  | Remarks
Civil |  | K.V. Dizon |  | L. Martillano
Structural |  | C. Autenico |  | L. Martillano
Architectural |  | J. Urbi |  | J. Carreon
Mechanical |  |  |  | V.E. Ting
Sanitary |  |  |  | V.E. Ting
Fire Protection |  |  |  | V.E. Ting
Electrical |  |  |  | J. Alinas
Auxiliary |  |  |  | J. Alinas
FDAS |  |  |  | J. Alinas
Surveyor |  | J. Urbi/G. Dela Fuente
Requested By: | [5 empty] | Inspected and Verified By:
Christian D. Autentico
Contractor - Site Engineer | [6 empty] | RNDC - Struct Coordinator / Inspector
Noted By: | [5 empty] | Noted By:
Daniel P. Briones | [6 empty] | Engr. Francis S. Santiago
Contractor - QAQC Engineer | [6 empty] | Contractor - Project Manager
Engr. Raul Francis C. Dizon | [6 empty] | Engr. Sheila L. Pacheco
Contractor - Project-in-Charge | [6 empty] | RNDC - Construction Manager
NOTE: Signature Over Printed Name and Date is Required

## Beams (Struct)
CONCRETE POURING REQUEST - BEAMS CHECKLIST | [7 empty] | 60/RNDC/WP101B/TB-IWR-ST-BC-001
TRADES
Building: | SUPERSTRUCTURE |  | Reference Number: |  |  | 60/RNDC/WP101B/TB-IWR-ST-BC-001 |  | MECHANICAL | M
Level: | Fifth Floor |  | Date of Request: |  |  | 2024-01-08 |  | ELECTRICAL | E
Area: | Zone 1 - GL MTA-LTA/1TA-6TA | [6 empty] | PLUMBING | PL
[8 empty] | FIRE PROTECTION | FP
[8 empty] | STRUCTURAL | ST
A. | Approved Drawings |  |  | Yes | No | N/A | Remarks | ARCHITECTURAL | A
A.1 | FCD | Date Issued: | [5 empty] | LANDSCAPE | L
A.2 | Approved BGCSP | Date Issued: | [5 empty] | INTERIOR DESIGN | ID
A.3 | Approved Cutting List | Reference Number:
DOCUMENT TYPE
B. | Formworks | [6 empty] | MATERIAL SAMPLE | MS
B.1 | Correct Gridlines / Reference Lines | [6 empty] | SHOP DRAWING | SD
B.2 | Correct Elevations | [6 empty] | WALL COMBINED SERVICES DRAWING | WCSD
B.3 | Cleanliness | [6 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
B.4 | Adequate Shoring, Braces and Supports | [6 empty] | METHODOLOGY | ME
B.5 | Approved Construction Key and Joints | [6 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
B.6 | Cambering | [6 empty] | REFLECTED CEILING PLAN | RCP
B.7 | Squareness and Plumbness | [6 empty] | TILE SETTING OUT PLAN | TSP
[8 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
C. | Rebar
C.1 | Passed Required Test
C.2 | Adequate Concrete Spacers
C.3 | Correct Quantity and Diameter
C.4 | Correct Splicing
C.5 | Approved Shear Bars / Shear Keys
C.6 | Rust / Scaling Free
C.7 | Dowels for Interior Walls
D. | MEPF Checklists | Reference Number:
D.1 | Electrical Checklist
D.2 | Plumbing / Sanitary Checklist
D.3 | Fire Protection Checklist
D.4 | Embedment
D.5 | As-Built Provided
E. | During Concreting
E.1 | Adequate Equipments on-site
E.2 | Concrete Vibrator with Back-up
E.3 | Pouring Guard For All Trades
D.1 | Post-Concreting
D.1 | Applied Curing Compound
D.2 | Passed Concrete Test
D.2 | Achieved Required Time Prior to Stripping
Observations and Comments
Requested By: |  |  |  |  | Verified By:
Contractor - Site Engineer | [5 empty] | RNDC - Struct Coordinator / Inspector
Noted By: |  |  |  |  | Noted By:
Daniel P. Briones | [5 empty] | Engr. Francis S. Santiago
Contractor - QAQC Engineer | [5 empty] | Contractor - Project Manager
Engr. Raul Francis C. Dizon | [5 empty] | Engr. Sheila L. Pacheco
Contractor - Project-in-Charge | [5 empty] | RNDC - Construction Manager
NOTE: Signature Over Printed Name and Date is Required

## Suspended Slab (Struct)
CONCRETE POURING REQUEST - SUSPENDED SLAB CHECKLIST | [9 empty] | 60/RNDC/WP101B/TB-IWR-ST-SS-001
TRADES
Building: | SUPERSTRUCTURE |  | Reference Number: |  |  |  | 60/RNDC/WP101B/TB-IWR-ST-SS-001 |  |  | MECHANICAL | M
Level: | Fifth Floor |  | Date of Request: |  |  |  | 2024-01-08 |  |  | ELECTRICAL | E
Area: | Zone 1 - GL MTA-LTA/1TA-6TA | [8 empty] | PLUMBING | PL
[10 empty] | FIRE PROTECTION | FP
[10 empty] | STRUCTURAL | ST
A. | Approved Drawings |  |  | Yes |  | No |  | N/A | Remarks | ARCHITECTURAL | A
A.1 | FCD | Date Issued: | [7 empty] | LANDSCAPE | L
A.2 | Approved BGCSP | Date Issued: | [7 empty] | INTERIOR DESIGN | ID
A.3 | Approved Cutting List | Reference Number:
DOCUMENT TYPE
B. | Formworks | [8 empty] | MATERIAL SAMPLE | MS
B.1 | Correct Gridlines / Reference Lines | [8 empty] | SHOP DRAWING | SD
B.2 | Correct Elevations | [8 empty] | WALL COMBINED SERVICES DRAWING | WCSD
B.3 | Cleanliness | [8 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
B.4 | Adequate Shoring, Braces and Supports | [8 empty] | METHODOLOGY | ME
B.5 | Approved Construction Key and Joints | [8 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
B.6 | Cambering | [8 empty] | REFLECTED CEILING PLAN | RCP
B.7 | Squareness and Plumbness | [8 empty] | TILE SETTING OUT PLAN | TSP
B.7 | Phenolic Boards not used more than 3 times | [8 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
C. | Rebar
C.1 | Passed Required Test
C.2 | Adequate Concrete Spacers
C.3 | Correct Quantity and Diameter
C.4 | Correct Splicing
C.5 | Approved Shear Bars / Shear Keys
C.6 | Rust / Scaling Free
C.7 | Dowels for Interior Walls
D. | MEPF Checklists | Reference Number:
D.1 | Electrical Checklist
D.2 | Plumbing / Sanitary Checklist
D.3 | Fire Protection Checklist
D.4 | Embedment
D.5 | As-Built Provided
D.6 | Pipe Sleeve and Block Outs are Correct
E. | During Concreting
E.1 | Adequate Equipments on-site
E.2 | Concrete Vibrator with Back-up
E.3 | Pouring Guard For All Trades
D.1 | Post-Concreting
D.1 | Applied Curing Compound
D.2 | Passed Concrete Test
D.2 | Achieved Required Time Prior to Stripping
Observations and Comments
Requested By: |  |  |  |  | Verified By:
Contractor - Site Engineer | [6 empty] | RNDC - Struct Coordinator / Inspector
Noted By: |  |  |  |  | Noted By:
Daniel P. Briones | [6 empty] | Engr. Francis S. Santiago
Contractor - QAQC Engineer | [6 empty] | Contractor - Project Manager
Engr. Raul Francis C. Dizon
Contractor - Project-in-Charge | [6 empty] | RNDC - Construction Manager
NOTE: Signature Over Printed Name and Date is Required

## Columns and SW (Struct)
60/RNDC/WP101B/TB-IWR-ST-CSW-018
COLUMNS AND SHEAR WALLS CHECKLIST
TRADES
[10 empty] | MECHANICAL | M
Building: | SUPERSTRUCTURE |  |  |  |  | Reference Number: |  | 60/RNDC/WP101B/TB-IWR-ST-CSW-018 |  | ELECTRICAL | E
Level: | Ground Floor |  |  |  |  | Date of Request: |  | 2024-01-08 |  | PLUMBING | PL
Structure: | Shearwall | [8 empty] | FIRE PROTECTION | FP
[10 empty] | STRUCTURAL | ST
[10 empty] | ARCHITECTURAL | A
|  |  | Inspected By: Omicron |  |  | Inspected By: RNDC |  |  |  | LANDSCAPE | L
A. | Approved Drawings |  | Yes | No | N/A | Yes | No | N/A | Remarks | INTERIOR DESIGN | ID
A.1 | FCD | Date Issued:
A.2 | Approved BGCSP | Date Issued: | [7 empty] | DOCUMENT TYPE
A.3 | Approved Cutting List | Reference Number: | [7 empty] | MATERIAL SAMPLE | MS
[10 empty] | SHOP DRAWING | SD
B. | Formworks | [8 empty] | WALL COMBINED SERVICES DRAWING | WCSD
B.1 | Correct Gridlines / Reference Lines | [8 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
B.2 | Correct Height | [8 empty] | METHODOLOGY | ME
B.3 | Cleanliness | [8 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
B.4 | Squareness and Plumbness | [8 empty] | REFLECTED CEILING PLAN | RCP
[10 empty] | TILE SETTING OUT PLAN | TSP
C. | Rebar | [8 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
C.1 | Passed Required Test
C.2 | Adequate Concrete Spacers
C.3 | Correct Quantity and Diameter
C.4 | Correct Splicing and Development Lenghts
C.5 | Rust / Scaling Free
D. | MEPF Checklists | Reference Number:
D.1 | Electrical Checklist
D.2 | Plumbing / Sanitary Checklist
D.3 | Fire Protection Checklist
D.4 | Embedment
E. | During Concreting
E.1 | Adequate Equipments on-site
E.2 | Concrete Vibrator with Back-up
E.3 | Pouring Guard For All Trades (as needed)
D.1 | Post-Concreting
D.1 | Passed Concrete Test
D.2 | Achieved Required Time Prior to Stripping
Observations and Comments
Requested By: | [5 empty] | Verified By:
Christian D. Autentico
Contractor - Site Engineer | [6 empty] | RNDC - Struct Coordinator / Inspector
Noted By: | [5 empty] | Noted By:
Daniel P.Briones | [6 empty] | Engr. Francis S. Santiago
Contractor - QAQC Engineer | [6 empty] | Contractor - Project Manager
Engr. Raul Francis C. Dizon
Contractor - Project-in-Charge | [6 empty] | RNDC - Construction Manager
NOTE: Signature Over Printed Name and Date is Required

## Slab on grade
SLAB ON GRADE CHECKLIST | [11 empty] | 60/RNDC/WP101B/TB-IWR-ST-SOG-001
TRADES
Building: | SUBSTRUCTURE | [5 empty] | Reference Number: |  |  | 60/RNDC/WP101B/TB-IWR-ST-SOG-001 |  | MECHANICAL | M
Area: | Zone 8 - 12 (partial) | [5 empty] | Date of Request: |  |  | 2024-01-08 |  | ELECTRICAL | E
[12 empty] | PLUMBING | PL
[12 empty] | FIRE PROTECTION | FP
|  |  |  | Inspected By: Omicron |  |  | Inspected By: RNDC |  |  |  |  | STRUCTURAL | ST
A. | Approved Drawings |  |  | Yes | No | N/A | Yes |  | No | N/A | Remarks | ARCHITECTURAL | A
A.1 | FCD | Date Issued: | [9 empty] | LANDSCAPE | L
A.2 | Approved Columnation Plan | Date Issued: | [9 empty] | INTERIOR DESIGN | ID
A.3 | Approved Cutting List | Reference Number:
A.4 | Pit Plans | Date Issued: | [9 empty] | DOCUMENT TYPE
[12 empty] | MATERIAL SAMPLE | MS
B | Pre-Concreting | [10 empty] | SHOP DRAWING | SD
B.1 | Soil Poisoning | [10 empty] | WALL COMBINED SERVICES DRAWING | WCSD
[12 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
C. | Formworks | [10 empty] | METHODOLOGY | ME
C.1 | Correct Gridlines / Reference Lines | [10 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
C.2 | Correct Excavation Depth | [10 empty] | REFLECTED CEILING PLAN | RCP
C.3 | Cleanliness | [10 empty] | TILE SETTING OUT PLAN | TSP
C.4 | Squareness and Plumbness | [10 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
C.5 | Gravel Bedding / Lean Concrete
D. | Rebar
D.1 | Passed Required Test
D.2 | Adequate Concrete Spacers
D.3 | Correct Quantity and Diameter
D.4 | Correct Splicing and Development Lenghts
D.5 | Rust / Scaling Free
D.6 | Vertical Members Starter Bars
D.7 | Spacing of Rebars
E. | MEPF Checklists | Reference Number:
E.1 | Electrical Checklist
E.2 | Plumbing / Sanitary Checklist
E.3 | Fire Protection Checklist
E.4 | Embedment
F. | During Concreting
F.1 | Adequate Equipments on-site
F.2 | Concrete Vibrator with Back-up
F.3 | Pouring Guard For All Trades (as needed)
G | Post-Concreting
G.1 | Passed Concrete Test
Observations and Comments
Requested By: |  |  | Verified By: |  |  |  |  | Noted By:
Engr. Sheila L. Pacheco
Contractor - Site Engineer |  |  | RNDC - Structural Engr |  |  |  |  | RNDC - Construction Manager
Noted By:
Daniel P. Briones
Contractor - QC Engr.
Engr. Raul Francis C. Dizon |  |  | Engr. Francis S. Santiago
Contractor - Project-in-Charge |  |  | Contractor - Project Manager
NOTE: Signature Over Printed Name and Date is Required

## Foundation
FOUNDATION and FOOTING TIE BEAM CHECKLIST | [10 empty] | 60/RNDC/WP101B/TB-IWR-ST-FFTB-001
TRADES
Building: | SUBSTRUCTURE - FOOTING | [5 empty] | Reference Number: |  | 60/RNDC/WP101B/TB-IWR-ST-FFTB-001 |  | MECHANICAL | M
Area: | GL JBB-K1BB/8B-9B | [5 empty] | Date of Request: |  | 2024-01-08 |  | ELECTRICAL | E
[11 empty] | PLUMBING | PL
[11 empty] | FIRE PROTECTION | FP
|  |  |  | Inspected By: Omicron |  |  | Inspected By: RNDC |  |  |  | STRUCTURAL | ST
A. | Approved Drawings |  |  | Yes | No | N/A | Yes | No | N/A | Remarks | ARCHITECTURAL | A
A.1 | FCD | Date Issued: | [8 empty] | LANDSCAPE | L
A.2 | Approved Columnation Plan | Date Issued: | [8 empty] | INTERIOR DESIGN | ID
A.3 | Approved Cutting List | Reference Number:
A.4 | Pit Plans | Date Issued: | [8 empty] | DOCUMENT TYPE
[11 empty] | MATERIAL SAMPLE | MS
B | Pre-Concreting | [9 empty] | SHOP DRAWING | SD
B.1 | Soil Poisoning | [9 empty] | WALL COMBINED SERVICES DRAWING | WCSD
[11 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
C. | Formworks | [9 empty] | METHODOLOGY | ME
C.1 | Correct Gridlines / Reference Lines | [9 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
C.2 | Correct Excavation Depth | [9 empty] | REFLECTED CEILING PLAN | RCP
C.3 | Cleanliness | [9 empty] | TILE SETTING OUT PLAN | TSP
C.4 | Squareness and Plumbness | [9 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
C.5 | Gravel Bedding / Lean Concrete
D. | Rebar
D.1 | Passed Required Test
D.2 | Adequate Concrete Spacers
D.3 | Correct Quantity and Diameter
D.4 | Correct Splicing and Development Lenghts
D.5 | Rust / Scaling Free
D.6 | Vertical Members Starter Bars
D.7 | Spacing of Rebars
E. | MEPF Checklists | Reference Number:
E.1 | Electrical Checklist
E.2 | Plumbing / Sanitary Checklist
E.3 | Fire Protection Checklist
E.4 | Embedment
F. | During Concreting
F.1 | Adequate Equipments on-site
F.2 | Concrete Vibrator with Back-up
F.3 | Pouring Guard For All Trades (as needed)
G | Post-Concreting
G.1 | Passed Concrete Test
Observations and Comments
Requested By: |  |  | Verified By: | [6 empty] | Noted By:
Contractor - Site Engineer |  |  | RNDC - Structural Engr | [6 empty] | RNDC - Construction Manager
Noted By:
Contractor - QC Engr.
Engr. Raul Francis C. Dizon |  |  | Engr. Francis S. Santiago
Contractor - Project-in-Charge |  |  | Contractor - Project Manager
NOTE: Signature Over Printed Name and Date is Required

## Exterior Walls
60/RNDC/WP101B/TB-IWR-ST-EW-001
CONCRETE POURING REQUEST - EXTERIOR WALLS
TRADES
[9 empty] | MECHANICAL | M
Building: | SUBSTRUCTURE |  |  |  | Reference Number: |  | 60/RNDC/WP101B/TB-IWR-ST-EW-001 |  | ELECTRICAL | E
Level: | Lower Ground Floor |  |  |  | Date of Request: |  | 2024-01-08 |  | PLUMBING | PL
Area / Unit: | Zone 1 - 2 GL MTA-GTA/1TA-6TA | [7 empty] | FIRE PROTECTION | FP
[9 empty] | STRUCTURAL | ST
[9 empty] | ARCHITECTURAL | A
A. | Approved Drawings |  |  |  | Yes | No | N/A | Remarks | LANDSCAPE | L
A.1 | Architectural Plan | Date Issued: | [6 empty] | INTERIOR DESIGN | ID
A.2 | Structural Plan | Date Issued:
A.3 | EWSOP | Date Issued: | [6 empty] | DOCUMENT TYPE
[9 empty] | MATERIAL SAMPLE | MS
B. | Reference | [7 empty] | SHOP DRAWING | SD
B.1 | Correct Lay-outs | [7 empty] | WALL COMBINED SERVICES DRAWING | WCSD
B.2 | 1.0 m Offset | [7 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
[9 empty] | METHODOLOGY | ME
C. | Rebar | [7 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
C.1 | Correct Quantity and Diameter | [7 empty] | REFLECTED CEILING PLAN | RCP
C.2 | Correct Spacing | [7 empty] | TILE SETTING OUT PLAN | TSP
C.3 | Correct Splicing Length | [7 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
C.4 | Adequate Concrete Spacer
C.5 | Adequate Dowel Emebdment (if post-installed)
C.6 | Approved Epoxy (if post-installed)
D. | Formworks
D.1 | Window Openings
D.2 | Door Openings
D.3 | Plumbness
D.4 | Adequate Shoring and Braces
E | MEPF
E.1 | Mechanical Block-outs
E.2 | Electrical Block-outs
E.4 | Electrical Embedments
Observations and Comments
Requested By: |  |  |  | Verified By: |  |  |  | Approved By:
Contractor - Site Engineer |  |  |  | RNDC - Structural Engr |  |  |  | RPDC - Construction Manager
RNDC - Architectural
Noted By:
RNDC - MEPF Engr
Contractor - QC Engr.
Engr. Raul Francis C. Dizon |  |  | Engr. Francis S. Santiago
Contractor - Project-in-Charge |  |  | Contractor - Project Manager
NOTE: Signature Over Printed Name and Date is Required

## Post-Concreting
POST-CONCRETING CHECKLIST
60/RNDC/WP101B/TB-IWR-ST-PCC-001
Building: | SUBSTRUCTURE | [6 empty] | Reference Number: |  |  | 60/RNDC/WP101B/TB-IWR-ST-PCC-001 |  |  | TRADES
Level: | Second Floor | [6 empty] | Date of Request: |  |  | 2024-01-08 |  |  | MECHANICAL | M
Area: | Zone 1 - GL MTA-LTA/1TA-6TA | [12 empty] | ELECTRICAL | E
[14 empty] | PLUMBING | PL
[14 empty] | FIRE PROTECTION | FP
[5 empty] | Inspected By: Omicron |  |  | Inspected By: RNDC
A. | Approved Drawings |  |  |  | Yes | No | N/A | Yes | No |  | N/A |  | Remarks | STRUCTURAL | ST
A.1 | FCD | Date Issued: | [11 empty] | ARCHITECTURAL | A
A.2 | Approved BGCSP | Date Issued: | [11 empty] | LANDSCAPE | L
[14 empty] | INTERIOR DESIGN | ID
B. | Structural Defects
B.1 | Visible Cracks | [12 empty] | DOCUMENT TYPE
B.2 | Honeycombs | [12 empty] | MATERIAL SAMPLE | MS
B.3 | Exposed Rebars | [12 empty] | SHOP DRAWING | SD
B.4 | Free From Stucked Debris | [12 empty] | WALL COMBINED SERVICES DRAWING | WCSD
[14 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
C. | Architectural Defects | [12 empty] | METHODOLOGY | ME
C.1 | Plumbness | [12 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
C.2 | Achieved Required Finish | [12 empty] | REFLECTED CEILING PLAN | RCP
C.3 | Achieved Required Elevations | [12 empty] | TILE SETTING OUT PLAN | TSP
C.4 | Achieved Required Openings | [12 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
D. | MEPF Checklists
D.1 | Correct Block-outs and Stub-outs | [12 empty] | Zone 17 - GL DBB/1BB-3BB
D.2 | Pipe-Sleeves | [12 empty] | Shearwall
D.3 | Markings Visible Under-Slab
D.4 | Embedments
E.1 | Post-Concreting
E.1 | Passed Concrete Test
E.2 | Achieved Required Time Prior to Stripping
Observations and Comments
Rectification Methodology (if any)
Requested By: |  |  | Verified By: | [6 empty] | Approved By:
Contractor - Site Engineer |  |  |  | RNDC - Structural Engr | [7 empty] | RNDC - Construction Manager
Noted By:
Daniel P. Briones |  |  |  | RNDC - Architectural
Contractor - QAQC Engineer
Engr. Raul Francis C. Dizon |  |  |  | RNDC - MEPF Engr
Contractor - Project-in-Charge
Engr. Francis S. Santiago
Contractor - Project Manager
NOTE: Signature Over Printed Name and Date is Required

## Stripping Form
60/RNDC/WP101B/TB-IWR-ST-FW-001
TRADES
[10 empty] | MECHANICAL | M
FORMWORK STRIPPING FORM | [9 empty] | ELECTRICAL | E
[10 empty] | PLUMBING | PL
[10 empty] | FIRE PROTECTION | FP
Building: | SUBSTRUCTURE |  |  | Reference Number: |  |  |  | 60/RNDC/WP101B/TB-IWR-ST-FW-001 |  | STRUCTURAL | ST
Level: | Second Floor |  |  | Date of Request: |  |  |  | 2024-01-08 |  | ARCHITECTURAL | A
Area: | Zone 1 - GL MTA-LTA/1TA-6TA | [8 empty] | LANDSCAPE | L
Structure: | Columns (2nd lift), Slab, Beams and Girders | [8 empty] | INTERIOR DESIGN | ID
|  |  |  | Yes |  | No |  | N/A | Remarks | DOCUMENT TYPE
A. | Concreting Cheklist |  | Checklist Ref. Number: | [6 empty] | MATERIAL SAMPLE | MS
|  |  | Date Casted: | [6 empty] | SHOP DRAWING | SD
[10 empty] | WALL COMBINED SERVICES DRAWING | WCSD
B. | Structure | [8 empty] | FLOOR COMBINED SERVICES DRAWING | FCSD
B.1 | Suspended Slab | 8 days | [7 empty] | METHODOLOGY | ME
B.2 | Beams and Girders | 14 days | [7 empty] | BEAM, GIRDER, CUTTING LIST | BGCL
B.3 | Foundation | 24 hrs | [7 empty] | REFLECTED CEILING PLAN | RCP
B.4 | Walls | 18 hrs | [7 empty] | TILE SETTING OUT PLAN | TSP
[10 empty] | BEAM, GIRDER, COLUMN & SLAB SEETING OUT PLAN | BGCSP
Retain permanent shoring for suspeded slab, girders and beams
Three (3) strong floors to support active structural floor
Observations and Comments
Requested By: |  |  |  |  | Verified By:
Contractor - Site Engineer | [6 empty] | RNDC - Struct Coordinator / Inspector
Noted By: |  |  |  |  | Noted By:
Daniel P. Briones | [6 empty] | Engr. Francis S. Santiago
Contractor - QAQC Engineer | [6 empty] | Contractor - Project Manager
Engr. Raul Francis C. Dizon
Contractor - Project-in-Charge | [6 empty] | RNDC - Construction Manager
NOTE: Signature Over Printed Name and Date is Required